YeBetWeg — የቤት-ወግ

Strategic Implementation Plan & Milestones

A 12-month phased roadmap with specific actions, timeframes, and measurable success metrics.

# Phase 1 — FOUNDATION (Month 0–1)

Goal: Infrastructure ready. No public content yet. Everything built to last.

## Week 1: Brand Setup

- Create all platform accounts: @YeBetWeg on TikTok, YouTube, Facebook Page + Group, Telegram Channel

- Design brand kit in Canva: logo, colors (#1A5276, #E67E22), fonts, 3 thumbnail templates

- Write channel bio in Amharic + English for all platforms — consistent, professional

- Set up Telegram bot via BotFather — run Prompt 3 in Claude.ai to generate the bot code

- Deploy bot to PythonAnywhere free tier — load 30 daily tips

## Week 2: Content System Setup

- Set up Canva Brand Kit with YeBetWeg colors, fonts, logos (20 min, one-time)

- Set up Buffer free account — connect TikTok, Facebook, YouTube

- Create Google Drive folder structure: /YeBetWeg/Scripts | /Footage | /Published

- Record a 'test' YouTube video — practice only, do not publish

- Run Prompt 1 (Master Weekly Content) in Claude.ai for Week 3's launch topics

## Week 3–4: Website Build

- Run Prompt 2 (Website Builder) in v0.dev — generate full Next.js codebase

- Create free Supabase project — run all SQL migrations from generated code

- Deploy to Vercel free tier — connect custom domain (buy yebetweg.com — ~$10/year, one-time investment)

- Populate all sample data in Supabase dashboard

- Test all pages on mobile (majority of Ethiopian users are mobile-first)

## Phase 1 Success Metrics

| METRIC | TARGET |
| --- | --- |
| All 4 social accounts created & branded | ✓ Done by Day 7 |
| Website live on Vercel | ✓ Done by Day 21 |
| Telegram bot auto-posting | ✓ Tested & live by Day 14 |
| Content batch for Month 1 ready | 4 YouTube scripts + 12 TikTok hooks |

# Phase 2 — LAUNCH (Month 1–3)

Goal: Consistent posting. First 1,000 followers. Community warmth established.

## Month 1: Soft Launch

- Post first YouTube video: Series 1 (Construction How-To) — topic: 'How to Read a Structural Drawing in Ethiopia'

- Post first 3 TikToks: Monday, Wednesday, Friday — repurposed clips from YouTube

- Go LIVE on Facebook for 30 min — introduce Betha and YeBetWeg concept

- Launch Telegram channel with a 'Free PDF' gift: 'Addis Construction Checklist' (generate via Claude.ai + Canva)

- Comment on 10 Ethiopian construction/engineering accounts per day — meaningful, visible engagement

## Month 2: Content Depth

- Publish first philosophy episode (Series 2): 'What Ethiopian Architecture Teaches Us About Community'

- Start the 'ዋጋ ዛሬ' (Price Today) TikTok series — post every Thursday

- Reach out to 3 Ethiopian engineers/architects for guest interviews (record via Google Meet for free)

- Cross-promote: Every YouTube video gets a Facebook post + Telegram teaser

## Month 3: Community Activation

- Host first Facebook Live Q&A — answer 10 construction questions from followers

- Launch Facebook Group 'Addis Construction Community' — invite all page followers

- Post first guest interview episode on YouTube

- Create and share first 'ዋጋ ዛሬ' weekly price roundup — publish to website blog simultaneously

## Phase 2 Success Metrics (End of Month 3)

| METRIC | TARGET | MINIMUM ACCEPTABLE | HOW TO MEASURE |
| --- | --- | --- | --- |
| TikTok followers | 1,000+ | 500 | TikTok analytics |
| YouTube subscribers | 300+ | 150 | YouTube Studio |
| Facebook page likes | 500+ | 250 | Meta Business Suite |
| Telegram subscribers | 300+ | 150 | Telegram stats |
| Website monthly visitors | 500+ | 200 | Vercel Analytics (free) |
| Average video views | 500+ per video | 200 | YouTube + TikTok analytics |

# Phase 3 — GROWTH (Month 4–6)

Goal: Monetization begins. Audience trust deepens. Marketplace activates.

## Month 4–5: Authority Building

- Publish a comprehensive YouTube series: '5-Part Guide to Building Your Home in Addis' — one video/week

- Launch Telegram Premium tier (500 ETB/month): access to weekly detailed price reports + premium tips

- Write 2 long-form blog posts per month on website — drives Google search traffic

- Apply for YouTube Partner Program once reaching 500 subscribers + 3,000 watch hours (accelerated path)

## Month 6: Marketplace Launch

- Activate property and material listings on website — invite 10 suppliers/agents to list for free initially

- Announce marketplace on all platforms — 'List Your Property Free for the First Month'

- Run first paid sponsorship: Accept a local construction material brand for a 4-video sponsorship deal

## Phase 3 Success Metrics (End of Month 6)

| METRIC | TARGET | REVENUE INDICATOR |
| --- | --- | --- |
| YouTube subscribers | 1,000+ (Partner threshold) | AdSense eligibility |
| Telegram premium subscribers | 20 paying members | 10,000 ETB/month |
| TikTok followers | 5,000+ | Brand deal eligibility |
| First sponsorship deal | 1 brand partner | 15,000–30,000 ETB |
| Website listings | 20 active listings | First commission transaction |

# Phase 4 — SCALE (Month 7–12)

Goal: Sustainable revenue. Recognized brand. YeBetWeg is the go-to Ethiopian construction + ideas platform.

- Reach 10,000 TikTok followers → apply for TikTok Creator Fund

- Launch YeBetWeg merchandise: branded hard hat stickers, notebooks (print-on-demand via local Addis printer)

- Host first live in-person event: 'YeBetWeg Construction Forum' in Addis — free entry, sponsored by a material brand

- Partner with Ethiopian engineering university departments for guest lecture crossovers

- Apply to Google News Initiative funding for journalism/media in Ethiopia

- Hire part-time assistant for content management (revenue now supports this)

## Year 1 End Targets

| PLATFORM/METRIC | FOLLOWER TARGET | REVENUE TARGET |
| --- | --- | --- |
| TikTok | 20,000+ | Creator Fund + brand deals |
| YouTube | 3,000+ | AdSense + sponsorships |
| Facebook | 5,000+ page likes | Brand partnerships + ads |
| Telegram | 2,000+ (200+ premium) | 100,000 ETB/month premium |
| Website monthly visits | 10,000+ | AdSense + listing commissions |
| TOTAL MONTHLY REVENUE | — | 150,000–300,000 ETB/month |